## Pt.1 - Critical Path
Activity | Description | Predecessors | Mean Days | A |  | B |  | C |  | D |  | E
A | Excavate |  |  | Days | P | Days | P | Days | P | Days | P | Days | P
B | Lay Foundation | A | 7 | 4 | 0.4 | 8 | 0.4 | 2 | 0.5 | 4 | 0.8 | 2 | 0.5
C | Rough Plumbing | B,D | 10 | 8 | 0.4 | 10 | 0.2 | 4 | 0.5 | 9 | 0.2 | 10 | 0.5
D | Frame | A | 3 | 11 | 0.2 | 12 | 0.4
E | Finish Exterior | D | 5
F | Install HVAC | C,E | 6

## Pt. 2 - Simulation
Simulation Experiment | Random Numbers |  |  |  |  | Activity Times | [5 empty] | Path Lengths |  |  | Project Duration | Duration > 27 days | Path Critical? |  |  | Activity | Description | Predecessors |  | A |  |  |  |  | B |  |  |  |  | C |  |  |  |  | D |  |  |  |  | E
| RN1 | RN2 | RN3 | RN4 | RN5 | A | B | C | D | E | F | ABCF | ADCF | ADEF |  |  | ABCF | ADCF | ADEF | A | Excavate |  |  | Days | P | Mapping (0-99) |  |  | Days | P | Mapping (0-99) |  |  | Days | P | Mapping (0-99) |  |  | Days | P | Mapping (0-99) |  |  | Days | P | Mapping (0-99)
1 | 57 | 14 | 76 | 45 | 89 | 8 | 8 | 4 | 4 | 10 | 5 | 25 | 21 | 27 | 27 | 0 | 0 | 0 | 1 | B | Lay Foundation | A |  | 4 | 0.4 | 0 | 39 | 39 | 8 | 0.4 | 0 | 39 | 39 | 2 | 0.5 | 0 | 49 | 49 | 4 | 0.8 | 0 | 79 | 79 | 2 | 0.5 | 0 | 49 | 49
2 | 60 | 82 | 77 | 22 | 45 | 8 | 12 | 4 | 4 | 2 | 5 | 29 | 21 | 19 | 29 | 1 | 1 | 0 | 0 | C | Rough Plumbing | B,D |  | 8 | 0.4 | 40 | 79 | 39 | 10 | 0.2 | 40 | 59 | 19 | 4 | 0.5 | 50 | 99 | 49 | 9 | 0.2 | 80 | 99 | 19 | 10 | 0.5 | 50 | 99 | 49
3 | 35 | 25 | 54 | 35 | 50 | 4 | 8 | 4 | 4 | 10 | 5 | 21 | 17 | 23 | 23 | 0 | 0 | 0 | 1 | D | Frame | A |  | 11 | 0.2 | 80 | 99 | 19 | 12 | 0.4 | 60 | 99 | 39
4 | 25 | 60 | 28 | 64 | 85 | 4 | 12 | 2 | 4 | 10 | 5 | 23 | 15 | 23 | 23 | 0 | 1 | 0 | 1 | E | Finish Exterior | D
5 | 94 | 23 | 55 | 92 | 93 | 11 | 8 | 4 | 9 | 10 | 5 | 28 | 29 | 35 | 35 | 1 | 0 | 0 | 1 | F | Install HVAC | C,E
6 | 97 | 16 | 94 | 52 | 94 | 11 | 8 | 4 | 4 | 10 | 5 | 28 | 24 | 30 | 30 | 1 | 0 | 0 | 1
7 | 74 | 49 | 36 | 94 | 15 | 8 | 10 | 2 | 9 | 2 | 5 | 25 | 24 | 24 | 25 | 0 | 1 | 0 | 0 | Average Project Duration Time |  |  | 26.6
8 | 0 | 94 | 76 | 88 | 78 | 4 | 12 | 4 | 9 | 10 | 5 | 25 | 22 | 28 | 28 | 1 | 0 | 0 | 1 | P (ABCF) in % |  |  | 40
9 | 14 | 10 | 12 | 0 | 10 | 4 | 8 | 2 | 4 | 2 | 5 | 19 | 15 | 15 | 19 | 0 | 1 | 0 | 0 | P (ADCF) in % |  |  | 0
10 | 56 | 58 | 25 | 43 | 51 | 8 | 10 | 2 | 4 | 10 | 5 | 25 | 19 | 27 | 27 | 0 | 0 | 0 | 1 | P (ADEF) in % |  |  | 70